Teacher answer booklet

Lesson 3:

Operational planning

OBJECTIVES:

- To identify time constraints to produce the media product.

- To identify the personnel involved and relevant facilities needed for the creation of a media product.

- To produce an operational plan (time constraints, personnel involved and relevant facilities) for a specific media product.

CHECK-IN TASK

Answer the questions in the boxes below, do not use your notes!

| Print media | Web/Online media | Interactive media |
| --- | --- | --- |
| Sponsorship | Crowdfunding | Corporate finance |
| Computer games industry | Advertising | Radio |

TASK 1: KNOWLEDGE AND UNDERSTANDING

- In the flow chart below, identify several reasons why each of these are considered a time constraint during media production. One has been done as an example.

- A production team must have the correct skills to produce a professional-quality product.

Which job/skills are required within a team to create a video game?

- programmers, - artists, - sound designers, - and testers with technical knowledge.

- Identify one advantage and one disadvantage to using experienced staff during media production.

Experienced personnel are often able to work more efficiently, solve problems quickly and produce higher-quality work. However, experienced professionals are usually more expensive to hire.

- Identify one advantage and one disadvantage to using inexperienced staff during media production.

Less experienced staff may require training, make more mistakes, or work more slowly, but they are often cheaper to employ.

- In the mind map below, identify different personnel required for a large scale film production.

- In the boxes provided below, how could each resource be used in a short horror film called "The Hoodie".

Props

Flashlight, notebook/diary, photograph, hoodie

Microphone

Boom microphone.

Computer

Editing workstation, storage computer.

Set

Abandoned corridor, lockers, graffiti-covered walls, dimly lit interior

Cameras

Digital cinema camera, DSLR camera, tripod-mounted camera

Software

Video editing software, image editing software, sound editing software, visual effects software

TASK 2: GUIDED PRACTICE

Case study A

Zuu Productions are developing a new video game called Island of Forbidden Skulls which will be released on PS5. They are also releasing a printed version of a walkthrough guide that can be purchased in shops.

- Why do the Zuu Productions need access to a sound recording and design studio?

To provide facilities for recording voiceovers, creating sound effects, and composing music for the game.

- Why do the Zuu Productions need access to project management software?

Tools for project management include task tracking, and collaboration among team members.

- Why do the Zuu Productions need access to a game engine?

The software framework or engine used to create and run the game. Popular game engines include Unity, Unreal Engine, and proprietary engines developed by some studios.

- Why do the Zuu Productions need an editorial office?

A physical workspace or office for the magazine's editorial team, writers, editors, and layout designers to collaborate and work on content.

- Why do Zuu Productions need personnel responsible for photography and artwork?

To produce high-quality images, illustrations, and artwork to accompany articles and enhance the visual appeal of the magazine.

- Why might Zuu Productions need to use digital publishing tools?

They can release a digital version of a walkthrough guide that can be accessed on digital devices such as smartphones and tablets.

Case study B

A small media company called Vision Spark Productions has been hired to create a promotional video and social media campaign for a new extreme sports energy drink called “Volt Rush.”

The final media product will include a 2-minute promotional video, short clips for social media, posters and digital advertisements. The company has a budget of £10,000, a production deadline of 6 weeks and a small production team.

Filming will take place at a skate park, a recording studio and a classroom converted into an editing suite. The production team plans to use DSLR cameras, microphones, computers, editing software, props such as skateboards and branded clothing and a custom-built set for indoor interview scenes.

- What is the main time constraint in this scenario?

The main time constraint is the 6-week production deadline.

- Why could filming at multiple locations create time problems?

Multiple locations may increase travel time, setup time, scheduling difficulties and delays

- Give two production tasks that must be completed before the deadline.

- filming, - editing, - poster design, - sound recording, - exporting videos, - social media preparation

- How could delays affect the final media product?

Delays could: - reduce quality, - rush editing, - miss release dates, - or increase stress and costs.

- Suggest one way the production team could save time.

- create a filming schedule, - reduce locations, - assign clear staff roles, - or film multiple scenes in one day.

- Name three different job roles that may be needed for this production.

- camera operator, - editor, - sound technician, - graphic designer, - director, - actor/presenter, - social media manager.

- Why would the production need people with video editing skills?

Editing skills are needed to: - cut footage, - add transitions, - include sound/music, - and create professional final videos.

- Why might experienced staff be important during filming?

Experienced staff can: - solve problems quickly, - work efficiently, - and improve production quality.

- Explain one problem that could happen if there are not enough staff members.

Too few staff members may: - slow production, - increase workload, - cause mistakes, - or delay deadlines.

- Why may smaller productions ask staff to complete multiple roles?

- save money, - reduce staffing costs, - manage limited budgets.

- Identify one facility mentioned in the scenario.

Recording studio, editing suite, skate park

- Name two pieces of equipment that will be used during production.

DSLR cameras, microphones, computers.

- What are props and how are they being used in this production?

Props are objects used in productions to support realism and branding. In this scenario, skateboards and branded clothing are used as props.

- Why are computers important for this media project?

video editing, graphic design, sound editing and exporting final products.

- Name one type of software the team may use and explain its purpose.

- Adobe Premiere Pro — used for video editing. - Adobe Photoshop — used for poster design. - Audacity — used for editing sound.

- Why might the production team build a set for interview scenes?

A set helps create: - a professional environment, - visual consistency, - and better control over lighting and filming conditions.

TASK 3: INDEPENDENT PRACTICE

A media production company, Bright Frame Media, has been commissioned to create a promotional video for a new roller coaster opening at a theme park.

The video will be used on:

- social media platforms

- the theme park website

- local television advertising

- digital screens around the park

Before production begins, the production team must evaluate several planning factors to ensure the project can be completed successfully.

The Production Manager says:

"We need to make sure we have enough time, the right people, and the necessary facilities and resources before filming starts."

Question 1

Why must time constraints be considered when planning the promotional video?

- Productions must be completed by agreed deadlines - Different production stages require time to complete - Delays may affect the final release date - Schedules must be organised carefully - The video must be completed before the roller coaster officially opens to the public.

Question 2

How could production delays affect the project?

- Deadlines may be missed - Additional costs may be incurred - Marketing opportunities may be lost - Resources may need to be rebooked - If filming is delayed, the theme park may not have promotional material ready for launch day

Question 3

Why is it important to create a production schedule?

- Helps organise tasks in the correct order - Ensures staff know when work must be completed - Improves project management - Helps meet deadlines - Filming, editing, and publishing activities can be coordinated effectively

Question 4

Why must personnel requirements be considered during planning?

- Productions require people with different skills - Staff availability must be considered - The number of staff affects costs and scheduling - Different roles are needed at different stages - The project may require camera operators, editors, and presenters

Question 5

Why are skills and experience important when selecting personnel?

- Experienced staff may produce higher-quality work - Specialist skills may be required - Fewer mistakes are likely to occur - Production tasks may be completed more efficiently - Experienced editors may produce a more professional final video

Question 6

What problems could occur if the production team does not have enough staff?

- Work may take longer to complete - Staff may become overloaded - Production quality may be affected - Deadlines may be missed - A small team may struggle to film multiple attractions at the same time

Question 7

Why should facilities be considered when planning?

- Some productions require specialist facilities - Facilities may need to be booked in advance - Availability can affect scheduling - Costs may need to be included in the budget - Editing suites may be needed to produce the final promotional video

Question 8

Why are locations an important planning factor?

- Locations must be suitable for filming - Permission may be required - Access arrangements must be organised - Environmental factors may affect filming - Filming around members of the public may create challenges

Question 9

Why should equipment requirements be identified during planning?

- Equipment availability affects production - Different productions require different equipment - Equipment may need to be hired - Costs must be considered - Cameras, microphones, and lighting equipment may be needed to create high-quality footage

Question 10

Why should software requirements be considered?

- Software may be needed for editing and production - Different tasks require different software packages - Licences may need to be purchased - Software availability can affect timescales - Video editing software will be required to create the finished advertisement

Question 11

Why should props and set requirements be considered?

- Some productions require additional materials - Props help create the intended message - Costs may need to be included in the budget - Resources must be available when needed - Promotional scenes may require branded merchandise and signage

Question 12

The theme park wants aerial footage of the roller coaster.

What additional planning considerations may be required?

- Specialist equipment may be needed - Additional personnel may be required - Permissions may need to be obtained - Costs may increase - Drone operators may need specific qualifications or experience

Question 13

The production company only has one experienced editor available.

How could this affect planning?

- Editing may take longer - The editor's availability must be managed carefully - Project deadlines may be affected - Alternative staffing arrangements may be needed - Other stages of production may need to be adjusted around the editing schedule

TASK 4: EXAM STYLE QUESTION

Scenario A media company called Pulse Interactive is producing a live-streamed charity gaming event to raise money for a local children’s hospital. The production will include live gameplay, interviews with guests and social media highlights. The event must be completed and streamed within one weekend. The production team includes two camera operators, one sound technician, one editor and several volunteers. The company will use a studio space, gaming computers, cameras, microphones, lighting equipment and streaming software.

Command word alert!

- Explain means to give a detailed account including reasons or causes.

Explain how time constraints, personnel, and facilities/resources could affect the production of the Pulse Interactive charity gaming event.

(6 marks)

Mark Scheme Level 3 (5–6 marks) - Detailed explanation of time constraints, personnel, and facilities/resources. - Clear application to the scenario. - Good understanding of how production may be affected. - Uses relevant media terminology accurately. Level 2 (3–4 marks) - Some explanation of at least two areas. - Some reference to the scenario. - Ideas may lack detail or development. Level 1 (1–2 marks) - Basic comments about one or more areas. - Limited explanation and little connection to the scenario. 0 Marks - No relevant response. Indicative Content Students may include: - limited weekend timeframe causing pressure, - live streaming increasing risk of mistakes, - importance of skilled camera and sound staff, - volunteers having less experience, - need for reliable studio facilities, - importance of gaming computers and streaming software, - equipment failures affecting the broadcast. Model Answer (6 Marks) The production has strong time constraints because the gaming event must be filmed and streamed within one weekend. This gives the team limited time to set up equipment, rehearse interviews, and edit social media highlights. Any technical problems during the live stream could cause delays because there is little time to fix issues. Personnel are important because the production needs skilled camera operators and a sound technician to ensure the stream looks and sounds professional. Since volunteers are also involved, some staff may have limited experience, which could increase the chance of mistakes during the live event. Facilities and resources are essential for the production. The studio space provides an organised environment for filming, while gaming computers, cameras, and microphones are needed for the live stream. Streaming software and editing software help broadcast and produce highlights professionally. If any equipment fails, the quality of the event could be reduced. Top of Form Bottom of Form

Terms of Use: Copyright Notice

© SIMPLY TEACH 2026

These Terms of Use govern the use of any material, content, or intellectual property provided by Simply Teach. By accessing or using the Material provided by Simply Teach, you agree to be bound by these Terms of Use.

- Copyright Notice: All Material provided by Simply Teach is protected by copyright laws. All rights are reserved by Simply Teach.

- Non-Redistribution: You may not redistribute, reproduce, republish, transmit, distribute, or otherwise use the Material provided by Simply Teach without prior written permission from Simply Teach.

- No Public Domain Usage: The Material provided by Simply Teach is not released into the public domain. You may not use, modify, or distribute the Material in any way that would place it in the public domain.

- Intellectual Property Rights: All intellectual property rights in the Material, including but not limited to copyrights, trademarks, patents, and trade secrets, belong to Simply Teach. You agree not to infringe upon these rights in any way.

Contact Information: If you have any questions about these Terms of Use, please contact Simply Teach at info@mysimplyteach.co.uk or visit our Facebook page.

By accessing or using the Material provided by Simply Teach, you acknowledge that you have read, understood, and agree to be bound by these Terms of Use. If you do not agree to these terms, you may not access or use the Material.